## WEB PORTAL DEMO PLAN
| PROJECT TITLE |  | START DATE
| WEB PORTAL DEMO |  | 2024-10-18 |  |  | PROJECT DURATION
| PROJECT MANAGER |  |  |  |  | in days
|  |  | 2024-11-08 |  |  | 16
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | TÌM HIỂU CÁC NỘI DUNG LIÊN QUAN WEB-PORTAL |  |  | 2024-10-18 | 2024-10-23 | 4 |  | Not Started
1.1 | ・BE：Java11 フレームワーク：Spring Boot、JPA ・FE：TypeScript、Vue.js、element-ui ・DB：MySQL ・Other：Microservices, Test Driven, Agile, Scrum, Secure Coding ・Unit Test: JUnit |  | nt_thanh | 2024-10-18 | 2024-10-23 | 4 |  | In Progress
1.2 | ・BE：Java11 フレームワーク：Spring Boot、JPA ・FE：TypeScript、Vue.js、element-ui ・DB：MySQL ・Other：Microservices, Test Driven, Agile, Scrum, Secure Coding ・Unit Test: JUnit |  | tv_thanh | 2024-10-18 | 2024-10-23 | 4 |  | Complete
1.3 | ・BE：Java11 フレームワーク：Spring Boot、JPA ・FE：TypeScript、Vue.js、element-ui ・DB：MySQL ・Other：Microservices, Test Driven, Agile, Scrum, Secure Coding ・Unit Test: JUnit |  | dx_tri | 2024-10-18 | 2024-10-23 | 4 |  | On Hold
1.4 | ・BE：Java11 フレームワーク：Spring Boot、JPA ・FE：TypeScript、Vue.js、element-ui ・DB：MySQL ・Other：Microservices, Test Driven, Agile, Scrum, Secure Coding ・Unit Test: JUnit |  | htp_ngan | 2024-10-18 | 2024-10-23 | 4
1.5 | ・BE：Java11 フレームワーク：Spring Boot、JPA ・FE：TypeScript、Vue.js、element-ui ・DB：MySQL ・Other：Microservices, Test Driven, Agile, Scrum, Secure Coding ・Unit Test: JUnit |  | hx_thanh | 2024-10-18 | 2024-10-23 | 4
1.6 | – Tạo Basic Design , new project + upload gitlab |  | tt_tuan | 2024-10-18 | 2024-10-23 | 4 | "https://gitlap.brycen.com.vn/"
2 | PROJECT LAUNCH & EXECUTION |  |  | 2024-10-24 | 2024-11-08 | 12
2.1 | - Tìm hiểu, hỗ trợ demo. ・BE：Java11 フレームワーク：Spring Boot、JPA ・FE：TypeScript、Vue.js、element-ui ・DB：MySQL ・Other：DDD, Microservices, Test Driven, Agile, Scrum, Secure Coding ・Unit Test: JUnit |  | tt_tuan | 2024-10-24 | 2024-11-08 | 12
2.2 | – Xây dựng chức năng CRUD USER + Unitest |  | tv_thanh | 2024-10-24 | 2024-11-08 | 12
2.3 | – Xây dựng chức năng CRUD Teams + Unitest |  | dx_tri, htp_ngan | 2024-10-24 | 2024-11-08 | 12
2.4 | – Xây dựng chức năng CRUD Roles + Unitest |  | nt_thanh, hx_thanh | 2024-10-24 | 2024-11-08 | 12
Formulas:
DURATION in days = IF([START DATE]=0,0,IF(WEEKDAY([START DATE],2)>5,0,IF(WEEKDAY([END DATE],2)>5,0,NETWORKDAYS([START DATE],[END DATE]))))